TENDER SYNOPSIS

Maharashtra State Electricity Distribution Company Limited (MSEDCL)

Tender No: CE-SPD/ADB/2026-27/T-13 (Nagpur Zone)  |  Version 2

Date of Issue: 19 May 2026

# 1. Basic Tender Particulars

| Parameter | Details |
| --- | --- |
| Tender Code | CE-SPD/ADB/2026-27/T-13 VERSION-2 |
| Issuing Authority | MSEDCL (Maharashtra State Electricity Distribution Company Limited) |
| Tender Type | Works Tender – Full Turnkey (Design, Supply & Installation) |
| Type of Bid | Single Stage Two-Envelope Process with e-Procurement |
| Funding Agency | Asian Development Bank (ADB) – Power Distribution Enhancement Program |
| Estimated Cost | Rs. 52,546.85 Lakhs (~Rs. 525.47 Crore) excl. GST |
| Tender Fee | Rs. 29,500/- (Rs. 25,000 + GST Rs. 4,500) |
| Budget Type | CAPEX ¦ Scheme: 0133 – Distribution Infrastructure & System Strengthening |
| Contact | Mr. Manik Gavali, EE (Special Projects) ¦ Mob: 9152303162 ¦ cespd.msedcl@gmail.com |

# 2. Key Dates

| Event | Date & Time (IST) |
| --- | --- |
| Release of RFB / Tender Sale Start | 19 May 2026 |  |
| Pre-Bid Meeting | 26 May 2026, 15:00 Hrs |  |
| Tender Sale End / Bid Submission Deadline | 09 June 2026, 15:00 Hrs |  |
| Opening – Technical Part (Envelope 1) | 09 June 2026, 16:00 Hrs |  |
| Opening – Financial Part (Envelope 2) | To be declared later |  |

# 3. Scope of Work

Full Turnkey – single-point responsibility covering survey, design, engineering, supply, erection, testing, commissioning and GIS asset tagging at Nagpur Zone, Maharashtra.

| Sr. | Category | Description |
| --- | --- | --- |
| i | New Substations | 33/11 kV, 22/11 kV, 66/33 kV Primary Substations (Partly/Fully-Outdoor) with 5 MVA & 10 MVA Power Transformers |
| ii | New HT Lines | New 33 kV, 22 kV and 11 kV lines |
| iii | Augmentation | Augmentation of Power Transformers, Substations and 33/22/11 kV lines |
| iv | Renovation | Renovation of existing distribution infrastructure |
| v | Distribution Transformers | New/Augmented DTs – 16 KVA to 315 KVA (single & three phase) |
| vi | LT Lines | Low Tension line works |
| vii | UG Cabling | HT/LT underground cabling including ABC cabling |
| viii | GIS Mapping & Asset Tagging | GPS-based mapping, tagging and integration into employer's GIS portal |

# 4. Eligibility & Qualification

## 4.1 Technical (past 7 years up to 31/03/2026 – Similar Works)

| Option | Requirement |
| --- | --- |
| A | 1 contract ≥ 70% of tender cost (~Rs. 368 Cr) |
| B | 2 contracts, each ≥ 40% (~Rs. 210 Cr each) |
| C | 3 contracts, each ≥ 30% (~Rs. 158 Cr each) |

Similar works: Electrical Transmission / Sub-transmission / Distribution sector — EHT/HT/LT Lines, Distribution Transformers or Substations. Pure LT-only experience NOT eligible. Works under Govt./Semi-Govt./Electricity Utility in India only.

## 4.2 Financial / Commercial

| Criterion | Requirement |
| --- | --- |
| Net Worth | Positive for each of the last 3 financial years |
| MAAT | ≥ 30% of tender cost (~Rs. 157.64 Cr) – best 3 of last 5 FY |
| Liquid Assets / Credit Facility | ≥ 10% of tender cost (~Rs. 52.55 Cr) – banker's certificate required |
| Pending Litigation | ≤ 50% of bidder's net worth |

JV (up to 3 partners): All partners individually meet Net Worth; collectively meet MAAT & LA. Lead partner ≥ 40%; others ≥ 25% each of MAAT/LA criteria.

# 5. Bid Security & Financial Requirements

| Item | Requirement |
| --- | --- |
| EMD / Bid Security | 2% of tender value OR Rs. 5 Cr (whichever LOWER) ¦ Form: Unconditional eBG from Scheduled Bank |
| Bank Details for BG | MSEDCL ¦ Bank of Maharashtra, Fort ¦ A/c: 20045003931 ¦ IFSC: MAHB0000002 |
| Bid Validity | 180 days from date of opening of Technical Part |
| Performance Security | 3% of Contract Price ¦ Valid till 30 days beyond Warranty Period |
| CPG – Supply (Part I) | 10% of Contract Price Part I (eBG) |
| CPG – Erection (Part II) | 3% of Contract Price Part II (eBG) |

# 6. Payment Terms

## 6.1 Advance Payment (Optional – Interest Bearing at SBI 1-yr MCLR)

| Contract Part | Advance | Conditions |
| --- | --- | --- |
| Supply (Part I) | 15% (2 × 7.5%) | BG of 110% per installment. 2nd release after utilization certificate of 1st. |
| Erection (Part II) | 10% (2 × 5%) | Site office mobilization required. BG of 110% per installment. 2nd after utilization certificate of 1st. |

## 6.2 Progressive Payments

| Installment | % | Trigger |
| --- | --- | --- |
| Supply – 1st | 60% | Receipt & acceptance at site + MDCC + insurance + quality certificate + dispatch evidence |
| Supply – 2nd | 30% | Erection, testing & commissioning + MB certification + material reconciliation (balance advance adjusted) |
| Supply – Final | 10% | Completion Certificate by Employer |
| Erection – 1st | 90% | Erection, testing & commissioning + MB certification + material reconciliation (100% advance adjusted) |
| Erection – Final | 10% | Completion Certificate + GIS asset tagging + asset takeover by Employer |

Payment Timeline: Released within 60 days of invoice. Delayed payment attracts interest at SBI 1-yr MCLR.

# 7. Price Variation / Escalation

Price Adjustment is applicable on Ex-works price component (less advance) only for specified materials. All other components – erection charges, inland freight & insurance – are FIRM for entire contract duration. Price Adjustment clause effective from contract signing date.

Note: If Contractor opts for NO advance, Price Adjustment is applicable on 100% contract value.

| Material / Item | Formula (Summary) | Index Source & Reference |
| --- | --- | --- |
| ACSR Conductor | P = Po + WA(AL–ALo) + WF(FE–FEo) WA = wt. of aluminium (MT/km); WF = wt. of steel (MT/km) AL = EC Grade Al Ingot price; FE = Galvanized steel wire price Prices: 30 days prior to delivery vs. 30 days prior to tender opening | IEEMA Circular: IEEMA/PVC/CONDUCTOR/2012 (eff. 1 Apr 2012) |
| Power Transformer (Station) | P = 0.01×Po(6 + 32×C/Co + 27×ES/ESo + 12×IS/ISo + 4×IM/IMo + 9×TO/TOo + 10×W/Wo) C=Copper rods; ES=CRGO lamination; IS=Steel plates; IM=Insulating material; TO=Transformer oil; W=CPI (2001=100) | IEEMA/PVC/PWR TRF_upto 400KV/2021 (eff. 1 Sep 2021) Indices: 1 month prior (material) ¦ 3 months prior (labour) to tendering & delivery |
| Distribution Transformer – Al wound (upto 2,500 kVA, 33 kV) | P = 0.01×Po(8 + 22×AL/ALo + 36×ES/ESo + 12×IS/ISo + 5×IM/IMo + 10×TO/TOo + 7×W/Wo) AL=LME CSP Al; ES=CRGO; IS=HR Coil 3.15mm; IM=Insulating material; TO=Transformer oil; W=CPI (2016=100) | IEEMA/PVC/DIST_AL_upto 2.5 MVA/2021 (eff. 1 Sep 2021) |
| Distribution Transformer – Cu wound (upto 2,500 kVA, 33 kV) | P = 0.01×Po(7 + 41×C/Co + 23×ES/ESo + 10×IS/ISo + 5×IM/IMo + 8×TO/TOo + 6×W/Wo) C=CC Copper rods; ES=CRGO; IS=HR Coil 3.15mm; IM=Insulating material; TO=Transformer oil; W=CPI (2016=100) | IEEMA/PVC/DIST_CU_upto 2.5 MVA/2021 (eff. 1 Sep 2021) |
| HT/LT Power & Control Cables (Al/Cu, PVC/XLPE, 1.1 kV to 33 kV) | Al cable: P = Po + AlF(Al–Alo) + CCFAl(PVCc–PVCco) + FeF(Fe–Feo) Cu cable: P = Po + CuF(Cu–Cuo) + CCFCu(PVCc–PVCco) + FeF(Fe–Feo) + AlF(Al–Alo) Factors (AlF, CuF, FeF etc.) published by IEEMA. Prices: 1st working day, 1 month prior to delivery vs. tendering | IEEMA/DIV/CAB/05 (eff. 1 Nov 2017) XLPE/PVC compound, steel armour, Al/Cu rod prices from IEEMA |
| 66/11 kV & 33/11 kV Switchgear, Circuit Breakers & Isolators | P = 0.01×Po(20 + 28×IS/ISo + 26×C/Co + 4×AL/ALo + 9×In/Ino + 13×W/Wo) IS=WPI Basic Metals (2011-12=100); C=LME Cu wire bars; AL=Busbar grade Al; In=Epoxy resin (indoor) / WPI Insulator (outdoor); W=CPI (2001=100) | IEEMA/PVC/MVSWGR/2019(R-2) (eff. 1 Jan 2019) IS: 3 months prior; C, AL, In: 1 month prior to tendering & delivery |
| Steel Structures (Lattice, Switchyard, ST&D network) | EC = EC1 – EC0; Fixed portion F = 0.15 EC1 = EC0×[0.15 + 0.18×HA1/HA0 + 0.40×LA1/LA0 + 0.16×Zn1/Zn0 + 0.11×L1/L0] HA=Heavy angle steel (≥150mm); LA=Lighter angle (≤110mm); Zn=Electrolytic zinc; L=CPI (2001=100) Subscript 0: 30 days before bid opening; Subscript 1: material at 2/3 period from award to dispatch; labour 60 days prior to dispatch | IEEMA(PVC)/TLT/(R)/02/2007 No PV for delay attributable to Contractor |
| Steel Tubular Poles & Polygonal Poles | Tubular: P = Po/100×(7 + 70×IS/ISo + 13×Zn/Zno + 10×W/Wo) Polygonal: P = Po/100×(9 + 64×IS/ISo + 13×Zn/Zno + 14×W/Wo) IS=HR Coil 3.15mm (4 months prior to delivery); Zn=Electrolytic zinc (1 month prior); W=CPI (2016=100, 3 months prior) | IEEMA(PVC)/TLT-2014(R-1) (eff. 1 Apr 2022) All raw material prices excl. GST |
| Aerial Bunched Cables (ABC) – LV/MV/HV | P = Po + Alph×(Al–Alo) + Alm×(Al–Alo) + CCFAlph×(Cc–Cco) + ... Al=LME Primary Al (incl. premium, converted Rs./MT); Cc=LV/HV XLPE compound; factors (Alph, Alm, CCFAlph etc.) published by IEEMA Prices: 1st working day, 1 month prior to delivery vs. tendering | IEEMA ABC circular (latest applicable) LME prices published by London Metal Bulletin |

Key Rules for Price Adjustment:

- PV NOT applicable on: advance payment component, erection charges, inland freight & insurance

- PV applicable from contract signing date; governed by L-2 schedule agreed between Employer & Contractor

- If contractor is delayed (own reasons): PV not applicable for delay period (schedule vs. actual dispatch, earlier used)

- All prices/indices as published by IEEMA; IEEMA circulars prevail in case of discrepancy

- Bidder to submit Price Adjustment Data in Form 16 with Technical Part of bid

# 8. Key Contract Conditions

| Condition | Details |
| --- | --- |
| Time for Completion | 24 months from Effective Date of Contract |
| Defect Liability Period | 12 months from Completion Certificate (extendable up to 24 months max.) |
| Liquidated Damages | 0.15% per week of unexecuted works value ¦ Cap: 5% of unexecuted works value |
| Quality Penalties | Major defects: 0.5% of contract cost ¦ Minor defects: 0% if rectified within 30 days |
| TPQMA Inspection | Pre-dispatch (3 weeks notice domestic, 6 weeks imports) + field inspections by employer-engaged agency |
| GIS / Asset Tagging | Mandatory – assets to be tagged & uploaded to employer's GIS portal before final payment |
| Works License | Valid electrical works license required; state-specific license within 2 months of award |
| Subcontracting | Sub-contractors from land-border countries must be registered with Competent Authority |

# 9. Key Documents – Technical Bid (Envelope 1)

- Bid Security eBG (Form 3B) + Bid Securing Declaration (Form 3A)

- Letter of Bid (Form 1) + Bidder Information Sheet (Form 2) + Power of Attorney (Form 4)

- Technical & Financial Qualification data: experience certificates, audited accounts (5 yrs), banker's certificate (Form 9)

- Make-in-India / Local Content Affidavit – Class-I local supplier (≥50% local content) (Form 6)

- JV documents if applicable: Joint Deed of Undertaking (Form 7/8), JV Agreement

- Compliance Undertaking + Deviations (Forms 11, 12) + Work Completion Schedule (Form 13)

- Price Adjustment Data (Form 16) + Integrity Pact (Form 21)

- NO prices to be disclosed in Envelope 1 – violation = outright rejection

Disclaimer: Prepared for internal reference from RFB Document CE-SPD/ADB/2026-27/T-13 Version 2 dated 19 May 2026. In case of any discrepancy, the original bidding document shall prevail. Refer www.mahadiscom.in for latest updates.